Onekof PM

Deployment, Migration & Go-Live Roadmap

Author: Oli T. Oli / DAPS Analytics     |     Date: 2026-05-23     |     Classification: Internal / Confidential

Executive Summary

| Milestone | Target Date | Status |
| --- | --- | --- |
| Tier 3 CI/CD live (Vercel + Supabase) | 2026-05-23 | DONE |
| Wave 5 INSA security hardening (P1–P5) | 2026-05-23 | DONE |
| EthioTelecom VM provisioned | 2026-06-07 | Pending |
| onekof.et domain registered | 2026-06-07 | Pending |
| Tier 2 go-live (Ethiopia self-hosted) | 2026-06-14 | Pending |
| Internal beta launch | 2026-06-21 | Pending |
| INSA certification submitted | 2026-06-28 | Pending |
| External / public beta | 2026-07-05 | Pending |
| First government pilot outreach | 2026-07-12 | Pending |
| Tier 1 sovereign pilot deployment | 2026-08-01 | Pending |

Part 1 — Current State (as of 2026-05-23)

Completed Infrastructure

| Component | State |
| --- | --- |
| Next.js 14 web app | Built — standalone Docker image ~300 MB |
| Prisma 5 + PostgreSQL 15 | 14 migrations applied on production DB |
| NextAuth.js v5 | Working — credentials + session management |
| CI workflow (GitHub Actions) | Green — build + type check on every push |
| Deploy workflow (GitHub Actions) | Green — auto-deploys to Vercel on master push |
| docker-compose.prod.yml | Ready for Tier 2 |
| Caddyfile (auto-SSL) | Ready for Tier 2 |
| setup-tier2-server.sh | Idempotent setup script ready |
| .env.production.example | Complete with all required keys |
| Mobile app (Expo/RN) | Feature-complete, EAS build linked |
| INSA security P1–P6 | DONE — Wave 5 closed today |
| EIPA copyright registration | Package submitted 2026-04-11 |

Remaining External Blockers

| Item | Blocker | Owner |
| --- | --- | --- |
| onekof.et domain | EthioTelecom/nic.et registration | Oli |
| EthioTelecom VM | Server procurement + SSH access | Oli |
| Resend domain verify | Needs .et domain first | Oli |
| INSA cert submission | Ready to submit — all gaps closed | Oli |

Part 2 — Three-Tier Deployment Architecture

| Tier 3 — Vercel + Supabase LIVE | URL: onekof.vercel.app → onekof.com DB: Supabase PostgreSQL + Session Pooler Redis: Upstash Deploy: GitHub push to master → auto-deploy Users: Global cloud SaaS, diaspora, international orgs |
| --- | --- |

| Tier 2 — Self-Hosted Ethiopia Target: 2026-06-14 | URL: onekof.et Server: EthioTelecom VM (Ubuntu 22.04, 4 vCPU, 8 GB RAM) DB: PostgreSQL 15 container Redis: Redis 7 container SSL: Caddy auto Let's Encrypt Users: Ethiopian businesses preferring data residency |
| --- | --- |

| Tier 1 — Air-Gapped Sovereign Target: 2026-08-01 | URL: Internal — customer's own network Delivery: Docker image via USB or ACR pull-token DB: Customer-managed PostgreSQL Auth: Fully isolated — no internet required Users: Ethiopian government, INSA-classified environments |
| --- | --- |

Part 3 — Week-by-Week Execution Plan

Week 1: May 25–31

Goal: Domain + Server Prep

☐  Register onekof.et at nic.et / EthioTelecom (bring: business cert, TIN)

☐  Contact EthioTelecom for VM quote: 4 vCPU / 8 GB / 100 GB SSD / Ubuntu 22.04

☐  Verify Vercel env vars (vercel env ls) — confirm all required keys present

☐  Tag current commit: git tag v1.0.0-beta && git push origin v1.0.0-beta

☐  Compile INSA certification submission package

☐  Submit INSA package to Technology House (or portal) by May 31

Week 2: June 1–7

Goal: Server Setup + Smoke Test

☐  SSH into EthioTelecom VM, harden SSH (disable password auth), configure UFW

☐  Clone repo: git clone https://github.com/daps-analytics/onekof-platform.git /opt/onekof

☐  Run: bash scripts/setup-tier2-server.sh (installs Docker, generates secrets, starts stack)

☐  Edit .env.production: fill in NEXTAUTH_URL, RESEND_API_KEY, SENTRY_DSN

☐  Tier 2 smoke test: all services healthy, signup + login + project creation works

☐  Verify blob encryption: uploaded files unreadable on disk (xxd check)

Week 3: June 8–14

Goal: DNS Cutover + Tier 2 Go-Live

☐  Point DNS A record: onekof.et → <server-ip>

☐  Point DNS A record: www.onekof.et → <server-ip>

☐  Add Resend SPF + DKIM + DMARC records, verify domain

☐  Restart Caddy → auto Let's Encrypt cert issued (~30 seconds)

☐  SSL Labs check: https://ssllabs.com → target A+ rating

☐  Security headers check: https://securityheaders.com → target A

☐  Test email delivery end-to-end (signup verification email)

☐  Take final Supabase backup before migration starts

☐  TIER 2 GO-LIVE DECLARATION — June 14

Week 4: June 15–21

Goal: Internal Beta

☐  Create beta organization, invite 5–10 internal / trusted users

☐  Configure Sentry alerts: any P0/P1 error → email + Telegram notification

☐  Configure UptimeRobot: downtime > 2 min → SMS alert

☐  Run k6 load test: 50 concurrent users, 5 min — target p95 < 500 ms

☐  Fix TypeScript errors: change ignoreBuildErrors to false, run pnpm dedupe

☐  Daily monitoring: docker compose ps, Sentry dashboard, disk usage

Week 5: June 22–28

Goal: INSA Follow-Up + Public Beta Prep

☐  Follow up on INSA submission (submitted May 30)

☐  Prepare 1-page data residency letter (Amharic + English)

☐  Update onekof.et landing page: signup CTA + pricing page

☐  Configure support@onekof.et email forwarding

☐  Build EAS production APK: eas build --platform android --profile production

☐  Distribute Android APK via Telegram channel + onekof.et/download

Week 6: June 29 – July 5

Goal: Public Beta Launch

☐  Final pre-launch checklist: load test pass, SSL A+, Sentry active, uptime monitor active

☐  Announce on LinkedIn in English + Amharic

☐  Post in Ethiopian tech Telegram groups

☐  Send email to beta waitlist

☐  Monitor Sentry continuously for first 4 hours

☐  Respond to all support inquiries within 4 hours

Week 7–8: July 6–19

Goal: Government Pilot Outreach

☐  Priority 1: Ministry of Innovation & Technology (MInT) — Director-General's office

☐  Priority 2: Ethiopian Investment Commission — IT Director

☐  Priority 3: Commercial Bank of Ethiopia — Digital Banking division

☐  Deliver: 1-page executive summary (Amharic + English), INSA cert, data residency letter

☐  Set up government demo environment with sample projects

☐  Present Tier 1 deployment brief: runs fully offline in their data center

Week 9–12: July 20 – August 15

Goal: Tier 1 Sovereign Deploy

☐  Tag release: git tag v1.0.0-tier1-20260720 && git push origin --tags

☐  Pull and save Docker image: docker save ... | gzip > onekof-tier1-v1.0.0.tar.gz

☐  Generate SHA256 hash for integrity verification

☐  Prepare USB delivery package: image + compose + env template + runbook (Amharic)

☐  On-site or remote: docker load, fill .env.production, docker compose up, run migrations

☐  TIER 1 GO-LIVE: first sovereign government deployment

Part 4 — Data Migration Plan (Tier 3 Cloud → Tier 2 Self-Hosted)

Migration window: approximately 2 hours. Each organization's data is isolated — migrating one org does not affect others.

Migration Steps

| Time | Action |
| --- | --- |
| T-48 hours | Pre-migration backup from Supabase using pg_dump --format=custom |
| T-24 hours | Dry run restore on staging Tier 2 — verify record counts match source |
| T-60 min | Notify affected users of maintenance window |
| T-30 min | Set NEXT_PUBLIC_MAINTENANCE=true → deploy (shows maintenance page) |
| T-0 | Final export from Supabase (captures last 30 min of data) |
| T+10 min | pg_restore into Tier 2 PostgreSQL container |
| T+15 min | Verify data counts match source exactly |
| T+20 min | Update DNS / give users new URL (onekof.et/[org-slug]) |
| T+25 min | Remove maintenance mode — NEXT_PUBLIC_MAINTENANCE=false → deploy |
| T+30 min | Org admin acceptance test — verify their data |
| T+60 min | Decommission org data from Supabase (data residency compliance) |

Part 5 — Rollback Plans

Tier 3 — Vercel (Instant)

vercel rollback

# Or via dashboard:

# Vercel → Project → Deployments → [previous] → ... → Promote to Production

Tier 2 — Self-Hosted

# 1. Stop app container

docker compose -f docker-compose.prod.yml stop onekof-web

# 2. Set previous image tag in .env.production

nano .env.production   # DOCKER_IMAGE=ghcr.io/daps-analytics/onekof-web:vPREVIOUS

# 3. Pull and restart

docker compose -f docker-compose.prod.yml pull onekof-web

docker compose -f docker-compose.prod.yml up -d onekof-web

Tier 1 — Sovereign

Load previous USB image: docker load < onekof-tier1-vPREVIOUS.tar.gz

Customer IT team restores from their local backup (procedure included in Tier 1 runbook).

Part 6 — Success Metrics

Beta Phase (Weeks 4–6)

| Metric | Target |
| --- | --- |
| Internal beta users | 10+ |
| Projects created | 5+ |
| Issues created | 50+ |
| P0 production incidents | 0 |
| Uptime | > 99.5% |
| Page load (p95) | < 2 seconds |
| API response (p95) | < 500 ms |

Public Beta Phase (Weeks 6–8)

| Metric | Target |
| --- | --- |
| Registered users | 50+ |
| Active organizations | 10+ |
| Weekly active users | 25+ |
| Email delivery rate | > 98% |
| P1 bug reports | < 5 |

Government Pilot Phase (Weeks 9–12)

| Metric | Target |
| --- | --- |
| Government orgs in pilot | 1–2 |
| Tier 1 deployments | 1 |
| INSA certification status | Submitted (awaiting response) |
| Enterprise contract conversations | 3+ active |

Part 7 — Open Items Tracker

| # | Item | Owner | Target | Status |
| --- | --- | --- | --- | --- |
| OI-1 | Register onekof.et domain | Oli | Jun 7 | Pending — do first |
| OI-2 | GitHub Actions CI/CD workflows | Oli | Done | Done |
| OI-3 | docker-compose.prod.yml | Oli | Done | Done |
| OI-4 | Caddyfile (auto-SSL) | Oli | Done | Done |
| OI-5 | GitHub repository secrets | Oli | Done | Done |
| OI-6 | INSA P1–P5 security gaps (Wave 5) | Oli | Done | Done |
| OI-7 | Provision EthioTelecom VM | Oli | Jun 7 | Pending |
| OI-8 | Run setup-tier2-server.sh | Oli | Jun 7 | Blocked on OI-7 |
| OI-9 | Tier 2 smoke test | Oli | Jun 14 | Blocked on OI-7 |
| OI-10 | Resend domain + email test | Oli | Jun 14 | Blocked on OI-1 |
| OI-11 | INSA certification submission | Oli | May 31 | Pending — this week |
| OI-12 | Remove ignoreBuildErrors: true | Oli | Jun 21 | Beta week |
| OI-13 | Load test (k6) | Oli | Jun 21 | Beta week |
| OI-14 | Mobile app store submission | Oli | Jun 28 | Pre-launch |
| OI-15 | Tier 1 offline USB package | Oli | Jul 20 | Gov pilot prep |
| OI-16 | Amharic ops runbook | Oli | Jul 20 | Gov pilot prep |
| OI-17 | Government pilot outreach | Oli | Jul 12 | Post-public-beta |
| OI-18 | First Tier 1 sovereign deployment | Oli | Aug 1 | Post-INSA cert |

Part 8 — Risk Register

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| EthioTelecom VM procurement delays | Medium | High | Use DigitalOcean/Linode as interim; migrate when ET VM ready |
| .et domain registration > 2 weeks | Medium | Medium | Launch on onekof.com interim; cut over to .et when ready |
| INSA certification takes > 6 weeks | Low | High | Start gov outreach in parallel — cert strengthens, not blocks |
| Blob encryption breaks existing files on upgrade | Low | High | decryptBlobBuffer is backward-compatible — dev passthrough for unencrypted files |
| Load spikes overwhelm single Tier 2 VM | Low | Medium | Caddy + Next.js handle ~500 concurrent on 4 vCPU; add scale if needed |
| Government procurement cycle longer than expected | High | Medium | Use time to onboard commercial customers — gov revenue is upside, not only path |

Part 9 — Immediate Actions This Week (May 25–31)

These three actions unblock everything else. Do them in order.

Action 1 — Register onekof.et (May 25)

Go to nic.et or EthioTelecom domain services in person.

Bring: Commercial registration certificate, TIN certificate, technical contact email.

Processing time: 3–7 business days. Start immediately.

Action 2 — Submit INSA Certification (May 26–27)

All P1–P5 security gaps are now closed. You are ready to submit.

Package: GO_LIVE_ROADMAP.md + MIGRATION_DEPLOYMENT_PLAN.md + Wave 4/5 security audit summary + EIPA confirmation.

Submit to INSA at Technology House or via their official portal.

Action 3 — Procurement Call with EthioTelecom (May 27–28)

Request: 1x Ubuntu 22.04 VM, 4 vCPU / 8 GB RAM / 100 GB SSD, static public IPv4.

Ports: 80 and 443 open inbound/outbound. Port 22 restricted to your IP.

Estimated cost: 3,000–8,000 ETB/month. Negotiate annual contract.

Document Owner: Oli T. Oli / DAPS Analytics   |   Next Review: 2026-06-14   |   Source of Truth: GO_LIVE_ROADMAP.md